## Stakeholder Emails
Name | Email | Company | System | Role
timothy kornish | timothy.kornish@mock_email.com | Contracter |  | Data Migraiton
mock contracter PM | contracter_pm@mock_email.com | Contracter |  | Project Manager
mock contracter QA | contracter_qa@mock_email.com | Contracter |  | Quality Assurance
mock contracter BA | contracter_ba@mock_email.com | Contracter |  | Business Analyst
mock client person 1 | mock_client_1_@mock_client_email.com | Client Company | MySQL | Account and Contact SME
mock client person 2 | mock_client_2_@mock_client_email.com | Client Company | MySQL | Contract SME
mock client person 3 | mock_client_3_@mock_client_email.com | Client Company | Salesforce | Product SME
mock client person 4 | mock_client_4_@mock_client_email.com | Client Company |  | Project Manager
mock client person 5 | mock_client_5_@mock_client_email.com | Client Company |  | Salesforce Apex Dev lead

## Source Data Setup Runbook
Step in Process | Owner | State | Notes on Process Step | Script Name | Script transformation time | Script record upload time | Total Run Time | Total Records | Records - Success | Records - Fallout | Runtime Notes
1 | Timothy Kornish | Completed | Download Account CSV mock data from Mockaroo |  | NA | NA | NA | 1000 | NA | NA
2 | Timothy Kornish | Completed | Download Contact CSV mock data from Mockaroo |  | NA | NA | NA | 3000 | NA | NA
3 | Timothy Kornish | Completed | Download Contract CSV mock data from Mockaroo |  | NA | NA | NA | 3000 | NA | NA
4 | Timothy Kornish | Completed | Download Contract Lines CSV mock data from Mockaroo |  | NA | NA | NA | 9000 | NA | NA
5 | Timothy Kornish | Completed | Add account_number_external_id column to contact csv | align_contacts_to_accounts.py |  |  |  | 3000 | 3000 | 0
6 | Timothy Kornish | Completed | Add account_number_external_id column to contract csv | align_contracts_to_accounts.py |  |  |  | 3000 | 3000 | 0
7 | Timothy Kornish | Completed | Add contract_line_number column to contact lines csv | generate_contract_lines.py |  |  |  | 9000 | 9000 | 0
8 | Timothy Kornish | Completed | generate account table in MySQL database | create_account_table.sql | NA | NA | NA | NA | NA | NA
9 | Timothy Kornish | Completed | generate contact table in MySQL database | create_contacts_table.sql | NA | NA | NA | NA | NA | NA
10 | Timothy Kornish | Completed | generate contract table in MySQL database | create_contracts_table.sql | NA | NA | NA | NA | NA | NA
11 | Timothy Kornish | Completed | generate contract lines table in MySQL database | create_contract_lines_table.sql | NA | NA | NA | NA | NA | NA
12 | Timothy Kornish | Completed | push csv of accounts into MySQL DB to act as source of data for migration | load_mock_account_data_to_source_mysql.py |  |  |  | 1000 | 1000 | 0
13 | Timothy Kornish | Completed | push csv of contacts into MySQL DB to act as source of data for migration | load_mock_contact_data_to_source_mysql.py |  |  |  | 3000 | 3000 | 0
14 | Timothy Kornish | Completed | push csv of contracts into MySQL DB to act as source of data for migration | load_mock_contract_data_to_source_mysql.py |  |  |  | 3000 | 3000 | 0
15 | Timothy Kornish | Completed | push csv of contract lines into MySQL DB to act as source of data for migration | load_mock_contract_line_data_to_source_mysql.py |  |  |  | 9000 | 9000 | 0

## Staging DB Runbook
Step in Process | Owner | State | Notes on Process Step | Script Name | Script transformation time | Script record upload time | Total Run Time | Total Records | Records - Success | Records - Fallout | Runtime Notes
1 | Timothy Kornish | Completed | generate account table in MSSQL staging database | create_source_account_staging.sql | NA | NA | NA | NA | NA | NA
2 | Timothy Kornish | Completed | generate contact table in MSSQL staging database | create_source_contact_staging.sql | NA | NA | NA | NA | NA | NA
3 | Timothy Kornish | Completed | generate contract table in MSSQL staging database | create_source_contract_staging.sql | NA | NA | NA | NA | NA | NA
4 | Timothy Kornish | Completed | generate contract lines table in MSSQL staging database | create_source_contract_lines_staging.sql | NA | NA | NA | NA | NA | NA
5 | Timothy Kornish | Completed | migrate source Account data from MySQL source DB to MSSQL staging DB | migrate_source_account_data_to_staging_mssql.py
6 | Timothy Kornish | Completed | migrate source Contact data from MySQL source DB to MSSQL staging DB | migrate_source_contact_data_to_staging_mssql.py
7 | Timothy Kornish | Completed | migrate source Contract data from MySQL source DB to MSSQL staging DB | migrate_source_contract_data_to_staging_mssql.py
8 | Timothy Kornish | Completed | migrate source Contract Line data from MySQL source DB to MSSQL staging DB | migrate_source_contract_line_data_to_staging_mssql.py

## Migration Runbook
Step in Process | Owner | State | Notes on Process Step | Script Name | Script transformation time | Script record upload time | Total Run Time | Total Records | Records - Success | Records - Fallout | Runtime Notes
| Timothy Kornish/Client |  | Go / no Go decision on migration
| Client |  | Verify Source Data Refresh complete
| Timothy Kornish |  | Updated Source Data migrated to Staging DB
| Timothy Kornish |  | Send email to stakeholders to keep all users out of the salesforce instance Inform all stakeholders the migration process is now beginning.
| Timothy Kornish |  | Purge record jobs in Salesforce to clear up space for migration. NOTE: this is generally not done in full size salesforce orgs, only done here in 5MB sandbox due to storage space limitations
| Timothy Kornish |  | Due to size limitation of SF org, only 50 accounts and related records will be migrated | 101_insert_sf_accounts.py |  |  |  | 50
| Timothy Kornish |  |  | 102_insert_sf_contacts.py |  |  |  | 117
| Timothy Kornish |  |  | 103_insert_sf_opportunities.py |  |  |  | 150
| Timothy Kornish |  | Turn off CPQ triggers
| Timothy Kornish |  |  | 104_insert_sf_quotes.py |  |  |  | 150
| Timothy Kornish |  |  | 105_insert_sf_quote_lines.py |  |  |  | 450
| Timothy Kornish |  | Turn on CPQ triggers
| Timothy Kornish |  |  | 106_update_sf_quotes.py |  |  |  | 150
| Timothy Kornish |  |  | 107_update_sf_orders_activate_order.py |  |  |  | 150
| Timothy Kornish |  |  | 108_update_sf_orders_contract_order.py |  |  |  | 150
| Timothy Kornish |  | Send email to stakeholders the migration process has finished and testing the migrated data may begin

## Backout Migration Runbook
Step in Process | Owner | State | Notes on Process Step | Script Name | Script transformation time | Script record upload time | Total Run Time | Total Records | Records - Success | Records - Fallout | Runtime Notes
| Timothy Kornish |  |  | 209_delete_sf_subscriptions.py
| Timothy Kornish |  |  | 208_delete_sf_contracts.py
| Timothy Kornish |  |  | 207_delete_sf_order_lines.py
| Timothy Kornish |  | step is now redundant, and handled by script 207_delete_sf_quote_lines.py, due to updates that need to happen on order lines before order or OrderItems can be deleted | 206_delete_sf_orders.py
| Timothy Kornish |  |  | 205_delete_sf_quote_lines.py
| Timothy Kornish |  |  | 204_delete_sf_quotes.py
| Timothy Kornish |  |  | 203_delete_sf_opportunities.py
| Timothy Kornish |  |  | 202_delete_sf_contacts.py
| Timothy Kornish |  |  | 201_delete_sf_accounts.py
| Timothy Kornish |  |  | purge_record_jobs.py